## Prog Inv
6490 MARINDUSTRY PLACE
SAN DIEGO, CA 92121
858-587-1901, F: 535-3704
LICENSE #444203
1. | Fill in all 'Red" cells on Subcontractor Progress Invoice Form |  |  |  |  | Invoice Date: | 2013-01-01
| This will auto-fill the other forms - retention invoice & releases |  |  |  |  | Your Invoice Number:
[6 empty] | Bycor Job#: |  | See your Sub-Contract
2. | Attach your company's own numbered invoice
3. | Attach back-up for new change orders being added to draw |  |  |  |  | (for BYCOR's use)
Cost Code:
4. | Attach a Conditional progress release (#1) |  |  |  |  | PM's Approval:
SUBCONTRACTOR PROGRESS INVOICE FORM
Project Name: |  | PROJECT NAME
Project Owner: |  | PROJECT OWNER NAME HERE
Project Address: |  | PROJECT ADDRESS HERE
Sub Name: |  | YOUR COMPANY NAME
Address: | [5 empty] | Tax ID #:
Phone#: |  |  | Email: |  |  | Fax #:
1 | Original Subcontract Amount: |  |  |  | 1
2 | Change Orders _____ to _____ |  |  |  | 0 |  |  | ATTACH BACK-UP FOR CHANGE ORDERS | 950
3 | Revised Subcontract Amount: |  |  |  | 1
4 | 0% | Percentage Complete to Date: |  |  | 0 |  |  | ENTER $ AMOUNT COMPLETE
Less GROSS previously billed (amt on line 4 of last invoice): |  |  |  |  | 0
| TOTAL GROSS AMOUNT THIS INVOICE: |  |  |  | 0
|  | Less 10% Retention on this Invoice: |  |  | 0
| NET INVOICE (release must match this amount): |  |  |  | 0 | Through: | 00/00/00 | THROUGH END OF MONTH
PLEASE STAPLE IN THIS ORDER - OUR INVOICE, YOUR INVOICE, CHANGE ORDERS, AND RELEASE
This Invoice Completed By:
Fax this invoice to (858) 535-3704 no later than the 20th of the month and
MAIL THE ORIGINAL

## Ret Inv
6490 MARINDUSTRY PLACE
SAN DIEGO, CA 92121
858-587-1901, F: 535-3704
LICENSE #444203
SEND THIS INVOICE ALONG WITH YOUR INVOICE FOR 100% LESS RETENTION | [5 empty] | Invoice Date: | 2013-01-01
[6 empty] | Your invoice number: | 0
1. | Attach your own numbered invoice |  |  |  |  | Bycor Job#: | +'Prog Inv'!H9
2. | Attach a Conditional Final release (#3) |  |  |  |  | (for BYCOR's use only)
Cost Code:
PM's Approval:
|  |  |  | SUBCONTRACTOR RETENTION INVOICE FORM |  |  |  | NOT FOR PROGRESS OR
|  |  |  | (SEND WHEN PROJECT IS 100% COMPLETE) |  |  |  | CHANGE ORDER BILLS…
Project Name: |  | PROJECT NAME | [5 empty] | RETENTION ONLY!
Project Owner: |  | PROJECT OWNER NAME HERE
Project Address: |  | PROJECT ADDRESS HERE |  |  | 0
Name: |  | YOUR COMPANY NAME
Address: |  | 0 |  |  | 0 | Tax ID #: | 0
Phone#: |  | 0 | Email: | +'Prog Inv'!E23 |  | Fax #: | 0
| Original Subcontract Amount: |  |  |  | 1
| Change Orders: |  |  |  | 0
| Revised Subcontract Amount: |  |  |  | 1
| 100% | Percentage of Contract Complete to Date: |  |  | 1
| FINAL RETENTION INVOICE |  |  |  | 0.1
PLEASE ATTACH IN THIS ORDER - OUR INVOICE FORM, YOUR INVOICE, THEN RELEASE
|  | This Invoice Completed By: |  | 0
Fax this invoice to (858) 535-3704 by the 20th of the month and
MAIL THE ORIGINAL

## #1 Prog Rel
0
PROJECT NAME
(1) CONDITIONAL WAIVER AND RELEASE UPON PROGRESS PAYMENT
(California Civil Code 8132)
NOTICE: THIS DOCUMENT WAIVES THE CLAIMANT'S LIEN, STOP PAYMENT NOTICE, AND PAYMENT BOND RIGHTS
EFFECTIVE ON RECEIPT OF PAYMENT. A PERSON SHOULD NOT RELY ON THIS DOCUMENT UNLESS SATISFIED THAT
THE CLAIMANT HAS RECEIVED PAYMENT.
IDENTIFYING INFORMATION
Name of Claimant: | YOUR COMPANY NAME
Name of Customer: | BYCOR GENERAL CONTRACTORS, INC.
Job Location: | PROJECT ADDRESS HERE |  |  | 0
Legal Owner: | PROJECT OWNER NAME HERE
Through Date: | 00/00/00
CONDITIONAL WAIVER AND RELEASE
This document waives and releases lien, stop payment notice, and payment bond rights the claimant has for labor and service
provided, and equipment and material delivered, to the customer on this job through the "Through Date" of this document. Rights
based upon labor or service provided, or equipment or material delivered, pursuant to a written change order that has been fully
executed by the parties to the date that this document is signed by the claimant, are waived and released by this document, unless
listed as an "Exception" below. This document is effective only on the claimant's receipt of payment from the financial institution
on which the following check is drawn:
Maker of Check: | BYCOR GENERAL CONTRACTORS, INC.
Amount of Check: | 0
Check Payable to: | YOUR COMPANY NAME
EXCEPTIONS
This document does not affect any of the following:
(1) | Retentions.
(2) | Extras for which the claimant has not received payment.
(3) | The following progress payments for which the claimant has previously given a conditional
waiver and release but has not received payment.
Date(s) of waiver and release:
| Amount(s) of unpaid progress payment(s): |  | 0
(4) | Contract rights, including:
(A) a right based on rescission, abandonment, or breach of contract, and
(B) the right to recover compensation for work not compensated by the payment.
SIGNATURE
Claimant's Signature:
Claimant's Title:
|  | Date of Signature: | 2013-01-01

## #3 Final Rel
0
PROJECT NAME
(3) CONDITIONAL WAIVER AND RELEASE UPON FINAL PAYMENT
(California Civil Code 8136)
NOTICE: THIS DOCUMENT WAIVES THE CLAIMANT'S LIEN, STOP PAYMENT NOTICE, AND PAYMENT BOND
RIGHTS EFFECTIVE ON RECEIPT OF PAYMENT. A PERSON SHOULD NOT RELY ON THIS DOCUMENT UNLESS
SATISFIED THAT THE CLAIMANT HAS RECEIVED PAYMENT.
IDENTIFYING INFORMATION
Name of Claimant: | YOUR COMPANY NAME
Name of Customer: | BYCOR GENERAL CONTRACTORS, INC.
Job Location: | PROJECT ADDRESS HERE |  |  | 0
Legal Owner: | PROJECT OWNER NAME HERE
CONDITIONAL WAIVER AND RELEASE
This document waives and releases lien, stop payment notice, and payment bond rights the claimant has for labor and
service provided, and equipment and material delivered, to the customer on this job. Rights based upon labor or service
provided, or equipment or material delivered, pursuant to a written change order that has been fully executed by the
parties prior to the date that this document is signed by the claimant, are waived and released by this document, unless
listed as an "Exception" below. This document is effective only on the claimant's receipt of payment from the financial
institution on which the following check is drawn:
Maker of Check: | BYCOR GENERAL CONTRACTORS, INC.
Amount of Check: | 0.1
Check Payable to: | YOUR COMPANY NAME
EXCEPTIONS
This document does not affect any of the following:
| Disputed claims for extras in the amount of: |  | $
SIGNATURE
Claimant's Signature:
Claimant's Title:
Date of Signature: